Business Case

| Project Name | Project Manager |
| --- | --- |
| Customer Experience (CX) Enhancements | Grace A Adebowale |
| Client | Duration |
| Flex Quick Retail | 6 Months |

| Executive Summary | This business case addresses the declining customer retention experienced by an e-commerce platform despite offering competitive pricing. The decline is negatively impacting revenue growth and brand reputation. The proposed project focuses on improving customer experience through enhanced website navigation, improved customer support, and real-time delivery tracking. |
| --- | --- |

| Problem Statement | Customers are experiencing following challenges: - Difficult and confusing website navigation. - Long customer wait time and getting generic responses. - Limited visibility into delivery tracking. |
| --- | --- |

| Proposed Solutions | - Redesign the website to improve usability and overall user experience. - Implement AI-driven chatbot to provide faster and more personalized customer support. - Introduce a real-time delivery tracking system to improve transparency and customer confidence. |
| --- | --- |

| Cost-Benefit Analysis | The estimated cost of the project is $20, 000. By implementing the proposed solution, the organization is expected to improve customer retention, which could result in an estimated 80% increase in revenue over time and improving retention rate. |
| --- | --- |

| Risk Assessment | - Resistance to change: Some customers may struggle with the new website interface. Mitigation: Communicate updates clearly through email and SMS notifications. - Data security concerns: Customers may worry about the safety of their personal information. Mitigation: Implement secure login processes and data protection measures. |
| --- | --- |

| Implementation Plan | The Customer Experience (CX) Enhancements project will be implemented over a 6-month period and executed in structured phases to minimize disruption to customers. Phases 1 (Month 1): Requirement Gathering and planning - Collect requirements through customer feedback, surveys, and stakeholder meetings. - Identify key system requirements and define project scope and success metrics. Phases 2 (Month 2 – 4): Design and development - Redesign the website interface to improve navigation and usability. - Developing and configure AI-driven chatbots to provide faster and more personalized customer support for real time assistance. - Implementing secure login and customer data protection measures. - Integrate a real-time tracking system with logistics partner and generate a tracking number and notifiy the customers via email or SMS. Phases 3 (Month 5) Testing and Training - Conduct system and security testing to ensure all components function correctly. - Perform user acceptance testing (UAT) with a selected group of customers. - Train customer support staff on managing chatbot interactions. Phases 4 (Month 6) Development and Monitoring - Launch the enhanced website and the tracking system to all customers. - Monitor the system performance and take note of the customer’s feedback. - Make necessary adjustments based on the customer feedback and the performance’s matrices. |
| --- | --- |